## Overview
Project Overview
As of Oct 1st
ID | Features | Web-App | Mobile-App | Overall
D00 | Framework, System and Environment Configuration | 70% | 50% | 60%
D01 | Application Users (sign in/sign up) | 100% | 20% | 60%
D02 | User Roles & admin function | 80% | 10% | 45%
D03 | Global Header & search function | 70% | 10% | 40%
D04 | Global Left Column | 100% | 25% | 62.5%
D05 | Welcome Screen | 100% | 25% | 62.5%
D06 | Jobs Overview Screen | 100% | 25% | 62.5%
D07 | Company/Department/Employee Jobs Screen | 100% | 20% | 60%
D08 | Job Details Screen | 100% | 10% | 55%
D08_A | Create Job Screen | 100% | 25% | 62.5%
D09 | Human Resources Screen | 100% | 25% | 62.5%
D10 | Employer Detail Screen / Employee journal screen | 100% | 25% | 62.5%
D11 | Report Screen [data from Quickbooks] | 100% | 25% | 62.5%
D12 | Equipment screen | 100% | 25% | 62.5%
D13 | Gmail integration | 100% | 25% | 62.5%
D14 | Calendar integration | 100% | 25% | 62.5%
D16 | CRM | 100% | 25% | 62.5%
D15 | Integration Testing for Launching | 100% | 0% | 50%
| Total | 95.56% | 21.94% | 58.75%
Status Overview
Project Completion Till Date | 58.75%
Project Remaining Development | 41.25%
Web Version
Completion Till Date | 95.56%
Remaining Development | 4.444%
Mobile Version
Completion Till Date | 21.94%
Remaining Development | 78.06%
Project Summary (as of October 1st, 2018):
Project is on the right schedule, we are keeping up with the plan to deliver both Web & Mobile versions to production by the end of 2018.
BA, Design Team and Development Team have spent time working on clarifications of business logic, as well as system design and develop simultaneously.
Though as we progress through the project, there are several modifications and further developments to the initial Specifications and Expectations sent over by the PO due to certain constraints in UX, UI and Coding.
Therefore, we would need Jan's support to speed up the reqs. review/feedback/approve process at the moment before we migrate all the UI/UW design from Web version to Mobile version to avoid double re-works.
That being said, we are constantly working on updating a documentation of System Specifications to present to PO for feedbacks and approvals.
The Demo is deployed to the Stage Environment. Detailed in sheet Beta Deliverables.

## Feature Development Status
OVERALL DEVELOPMENT PROGRESS
As of Oct 1 |  |  | Account for reviewing Beta Version: dan@samplename.com/123456
ID | Major Functions | Features | Reqs./UI Design Status | APIs Status (For Web & Mobile) | Web Front-End Dev. Status | Mobile Front-End Dev. Status | Back-end Integration Status | Estimated Overall Completion Percentage | Comments
D0 | Framework, System and Configuration | [6 empty] | 60% | Develop framework and setup environment for Development
D01 | Application Users (Sign in/Sign up) | Sign In | Approved | Done | Done | Not started | Done | 60% | Account for reviewing Beta version: dannguyen@gmail.com/123456Aa@ Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/316513387/preview + APIs: http://idsimpact.somotsoft.com/Help WIP Items: + Web Integrated: http://idsdemo.somotsoft.com:8080/signin
|  | Sign Up | Approved | Done | Done | Not started | Done | 60% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/316513386/preview + APIs: http://idsimpact.somotsoft.com/Help + Web Integrated: http://idsdemo.somotsoft.com:8080/signup
D02 | User Roles & Admin Functions | Account Settings | Company Settings - UI Done User Profile - UI Done System Customisation - Not started (not included in Beta) | Done | Done | Not started | Done | 60% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/320456915/preview WIP Items: + APIs: http://idsimpact.somotsoft.com/Help + Web Integrated: http://idsdemo.somotsoft.com:8080/admin/hrm/setting
|  | Notifications | UI Done | Not started | Not started | Not started | Not started | 30% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/320452364/preview Notes: UI Design for Beta version only. Will be updated with more Setting features.
|  | Integrations | UI Done | Not started | Not started | Not started | Not started | 25% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/319420086/preview
D03 | Global Header & Search Function | Global Header | Approved | Done | Done | Not started | Done | 60% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/307261426/preview + APIs: http://idsimpact.somotsoft.com/Help WIP Items: + Web Integrated: http://idsdemo.somotsoft.com:8080/home
|  | Basic Keyword Search | UI Done | Not started | Not started | Not started | Not started | 35% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/313321940/preview Notes: UI Design for Beta version only. Will be updated with more Search features.
|  | Advanced Search | Not started (not included in Beta) | Not started | Not started | Not started | Not started | 0%
D04 | Global Left Column | Global Left Column Note: Requires Clarifications for Task List | Approved | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/313321940/preview + APIs: http://idsimpact.somotsoft.com/Help WIP Items: + Web Integrated: http://idsdemo.somotsoft.com:8080/home
D05 | Home | Home | Approved | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/307261426/preview + APIs: http://idsimpact.somotsoft.com/Help + Web Integrated: http://idsdemo.somotsoft.com:8080/home
D06 | Jobs Summary Screen | Job Overview Screen | Approved | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/320452312/preview + APIs: http://idsimpact.somotsoft.com/Help + Web Integrated: http://idsdemo.somotsoft.com:8080/jobs/overview
D07 | Company/Department/Employee Jobs Screen | Company Jobs | Approved | Done | Done | Not started | Done | 60% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/320452324/preview + APIs: http://idsimpact.somotsoft.com/Help + Web Integrated: http://idsdemo.somotsoft.com:8080/jobs/allJobs
|  | Jobs by Employee | Approved | Done | Done | Not started | Done | 60% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/320452325/preview + APIs: http://idsimpact.somotsoft.com/Help WIP Items: + Web Integrated: http://idsdemo.somotsoft.com:8080/jobs/empJobs
|  | Department | Approved | Done | Done | Not started | Done | 60% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/320452327/preview + APIs: http://idsimpact.somotsoft.com/Help + Web Integrated: http://idsdemo.somotsoft.com:8080/jobs/deptJobs
D08 | Job Details Screen | View Map Details (clicking on Map will redirect to Google Maps) | UI Done | Done | In progress | Not started | Done | 60% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/320983950/preview + APIs: http://idsimpact.somotsoft.com/Help WIP Items: + Web Integrated: http://idsdemo.somotsoft.com:8080/jobs/detailsJobs/1
|  | Edit Customer Details - Pop-up Form | UI Done | Done | In progress | Not started | Done | 60% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/320967743/preview + APIs: http://idsimpact.somotsoft.com/Help WIP Items: + Web Integrated: http://idsdemo.somotsoft.com:8080/jobs/detailsJobs/1
|  | Edit Job Contacts - Pop-up Selection | UI Done | Done | In progress | Not started | Done | 60% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/320877717/preview + APIs: http://idsimpact.somotsoft.com/Help + Web Integrated: http://idsdemo.somotsoft.com:8080/jobs/detailsJobs/1
|  | Job Journals | View - UI Done Edit - Not started Add New - UI Done | Done | In progress | Not started | Done | 60% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/320877718/preview + APIs: http://idsimpact.somotsoft.com/Help + Web Integrated: http://idsdemo.somotsoft.com:8080/jobs/detailsJobs/1
|  | Job Accounting | Table Display - UI Done Row Details Hover - Not started | In progress | In progress | Not started | Done | 60% | WIP Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/320877719/preview + APIs: http://idsimpact.somotsoft.com/Help + Web Integrated: http://idsdemo.somotsoft.com:8080/jobs/detailsJobs/1
|  | Job Documents - View/Upload/Rename | UI Done | Done | In progress | Not started | Done | 60% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/320877720/preview + APIs: http://idsimpact.somotsoft.com/Help + Web Integrated: http://idsdemo.somotsoft.com:8080/jobs/detailsJobs/1
D08_A | Create job | Create Job Step 1 (Both Residential & Commercial Types) | Approved | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/320452313/preview + APIs: http://idsimpact.somotsoft.com/Help + Web Integrated: http://idsdemo.somotsoft.com:8080/jobs/createJobs
|  | Create Job Step 2 | Approved | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/320452315/preview + APIs: http://idsimpact.somotsoft.com/Help WIP Items: + Web Integrated: http://idsdemo.somotsoft.com:8080/jobs/createJobs
|  | Create Job Step 3 | Approved | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/320452316/preview + APIs: http://idsimpact.somotsoft.com/Help WIP Items: + Web Integrated: http://idsdemo.somotsoft.com:8080/jobs/createJobs
D09 & D10 | Human Resources Screen (Employee Management) | Employee Details | UI Done | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/320452381/preview + APIs: http://idsimpact.somotsoft.com/Help WIP Items: + Web Integrated: http://idsdemo.somotsoft.com:8080/admin/hrm/details
|  | List of Employees | Approved | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/320452376/preview + APIs: http://idsimpact.somotsoft.com/Help + Web Integrated: http://idsdemo.somotsoft.com:8080/admin/hrm
|  | Employee Selected | UI Done | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/320452377/preview + APIs: http://idsimpact.somotsoft.com/Help + Web Integrated: http://idsdemo.somotsoft.com:8080/admin/hrm
|  | Edit Employee Contact | UI Done | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/320452380/preview + APIs: http://idsimpact.somotsoft.com/Help + Web Integrated: http://idsdemo.somotsoft.com:8080/admin/hrm
|  | Add Employee | UI Done | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/320452378/preview + APIs: http://idsimpact.somotsoft.com/Help WIP Items: + Web Integrated: http://idsdemo.somotsoft.com:8080/admin/hrm/admin-add-employee
|  | Employee Journal | UI Done | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/320452381/preview + Web Integrated: http://idsdemo.somotsoft.com:8080/admin/hrm/details
D11 | Report Screen [Data from Quickbooks] | Standard Reports | UI Done | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/315963880/preview WIP Items: + Web Integrated: http://idsdemo.somotsoft.com:8080/report/standard
|  | List of Report Expand/Collapse (Example) | UI Done | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/315963879/preview
|  | Favourite Reports | UI Done | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/316185230/preview
|  | Report Details (Example) | UI Done | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/316219573/preview WIP Items: + Web Integrated: http://idsdemo.somotsoft.com:8080/report/standard/detail
|  | Customise Reports (Exapand/Collapse) | UI Done | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/316385854/preview + Web Integrated: http://idsdemo.somotsoft.com:8080/report/standard
D12 | Equipment Screen | Equipment List Note: UI does not include Barcode font. | Approved | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/313294514/preview + APIs: http://idsimpact.somotsoft.com/Help + Web Integrated: http://idsdemo.somotsoft.com:8080/equipment
|  | Add Equipment Popup Note: UI does not include Barcode font. | Approved | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/320452361/preview + APIs: http://idsimpact.somotsoft.com/Help + Web Integrated: http://idsdemo.somotsoft.com:8080/equipment
D13 | Gmail Integration | Mailbox (Default view) | Approved | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/313321940/preview + APIs: http://idsimpact.somotsoft.com/Help + Web Integrated: http://idsdemo.somotsoft.com:8080/mail
|  | Conversation View | Approved | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/320452332/preview + APIs: http://idsimpact.somotsoft.com/Help + Web Integrated: http://idsdemo.somotsoft.com:8080/mail
|  | Conversation Selected (Drop-down Options) | UI Done | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/320452331/preview + APIs: http://idsimpact.somotsoft.com/Help + Web Integrated: http://idsdemo.somotsoft.com:8080/mail
|  | Mail Compose Box | UI Done | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/320452330/preview + APIs: http://idsimpact.somotsoft.com/Help + Web Integrated: http://idsdemo.somotsoft.com:8080/mail
|  | Conversation Reply Box | UI Done | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/320452333/preview + APIs: http://idsimpact.somotsoft.com/Help + Web Integrated: http://idsdemo.somotsoft.com:8080/mail
|  | Contact Card (for Both External & Internal Contacts) | UI Done | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design for Internal: https://projects.invisionapp.com/d/main#/console/14757438/320452334/preview + UI Design for External: https://projects.invisionapp.com/d/main#/console/14757438/320477674/preview + Web Integrated: http://idsdemo.somotsoft.com:8080/mail
D14 | Calendar Integration | Calendar Display Note: Current UI Design does not include Time Tracking function for Job and Employee. Will be updated for later version. | Approved | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/313726919/preview + APIs: http://idsimpact.somotsoft.com/Help + Web Integrated: http://idsdemo.somotsoft.com:8080/calendar
|  | Calendar View for Day/Week/Month/Year | UI Done | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/313726920/preview + APIs: http://idsimpact.somotsoft.com/Help WIP Items: + Web Integrated: http://idsdemo.somotsoft.com:8080/calendar
|  | Create Event & Edit Event | UI Done | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design for Create Event: https://projects.invisionapp.com/d/main#/console/14757438/320452342/preview + UI Design for Edit Event: https://projects.invisionapp.com/d/main#/console/14757438/314238053/preview + APIs: http://idsimpact.somotsoft.com/Help WIP Items: + Web Integrated: http://idsdemo.somotsoft.com:8080/calendar
|  | Event Details (Quick View) Note: Event Details in Full View will be updated for later version. | UI Done | Done | Doing | Not started | Done | 62.5% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/313759274/preview + APIs: http://idsimpact.somotsoft.com/Help + Web Integrated: http://idsdemo.somotsoft.com:8080/calendar
D16 | Customer Relationship Management (CRM) | CRM Residential List | Approved | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/320452353/preview + APIs: http://idsimpact.somotsoft.com/Help + Web Integrated: http://idsdemo.somotsoft.com:8080/crm/residential
|  | CRM Commercial List | Approved | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/320452345/preview + APIs: http://idsimpact.somotsoft.com/Help + Web Integrated: http://idsdemo.somotsoft.com:8080/crm/commercial
|  | CRM Residential Contact Detail | UI Done | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/320452351/preview + APIs: http://idsimpact.somotsoft.com/Help + Web Integrated: http://idsdemo.somotsoft.com:8080/crm/residential
|  | CRM Commercial Contact Detail | UI Done | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/320452348/preview + APIs: http://idsimpact.somotsoft.com/Help + Web Integrated: http://idsdemo.somotsoft.com:8080/crm/commercial
|  | Edit CRM Residential Contact | UI Done | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/320452349/preview + APIs: http://idsimpact.somotsoft.com/Help + Web Integrated: http://idsdemo.somotsoft.com:8080/crm/residential
|  | Edit CRM Commercial Contact | UI Done | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design: https://projects.invisionapp.com/d/main#/console/14757438/320452347/preview + APIs: http://idsimpact.somotsoft.com/Help + Web Integrated: http://idsdemo.somotsoft.com:8080/crm/commercial
|  | Add CRM Contact (for both Residential and Commercial Types) | UI Done | Done | Done | Not started | Done | 62.5% | Completed Items: + UI Design for Residential: https://projects.invisionapp.com/d/main#/console/14757438/320452355/preview + UI Design for Commercial: https://projects.invisionapp.com/d/main#/console/14757438/320452354/preview WIP Items: + APIs: http://idsimpact.somotsoft.com/Help + Web Integrated: http://idsdemo.somotsoft.com:8080/crm/commercial/contact
D15 | Integration Testing for Launching | Integration Testing for Beta | [5 empty] | 50%
|  | Integration Testing for Final Production | [5 empty] | 0%
[7 empty] | Estimated Progress | 58.73%

## Beta Deliverables
Features to be deployed in Beta version (as of the end of September 2018)
ID | Major Functions | Deployed Features | Remaining Features (Deployed in Oct) | Notes
D0 | System and Configuration
D01 | Application Users (Sign in & Sign up Processes) | Sign In (for both Admin & Standard Users)
|  | Sign Up Notes: No User Role Seperation at Sign Up. First time signed up user will be default as Standard User. |  | Since we haven't finalized role separation at sign up, any user signing into the current system will have access to all available features.
D02 | User Roles & Admin Functions | Account Settings: - Company Settings: View/Edit/Change Logo - User Profile: View/Edit/Change Password/Phone Number/Avatar/Job Title | - Notifications - Integrations (google, sign up & in) - Permissions Settings for each User types (Company Admin, Page Admin, Standard User) | Current System Design does not provide UI for Permissions Settings for each User types since our team wants to provide a general demo for the customer without the hassle of setting up new company information and defining User roles at this stage. For Beta version, Admin user can set/edit User types for any accounts in the system.
D03 | Global Header & search function | Global Header: - Header Menus - Display Client Logo and IDS Logo | - Basic Keyword Search (free text) - Advanced Search | Requires further clarifications
D04 | Global Left Column | Global Left Column - User Information - Today's events - Inbox Unread Mails | - Task List | Requires further clarifications
D05 | Home | Home: - Jobs Summary - Sales Summary - Recently Entered Jobs
D06 | Jobs Summary Screen | Job Overview Screen: - Current Jobs - Current Month's Sales
D07 | Company/Department/Employee Jobs Screen | Company Jobs
Jobs by Employee
Department
D08 | Job Details Screen | View Map Details
Edit Customer Details - Pop-up Form
Edit Job Contacts - Pop-up Selection
Job Journals - Pop-up Add New
|  | Job Accounting | Row Details Hover for Job Accounting | Wireframes from customer received. UI to be developed for later version
Job Documents - View/Upload/Rename/Download
D08_A | Create Job | Create Job Step 1
Create Job Step 2
Create Job Step 3
D09 & D10 | Human Resources Screen (Employee Management) | Employee List
Employee Details
Employee Selected: - Delete - Export Data
Edit Employee
Add Employee
Employee Journal
D11 | Report Screen [data from Quickbooks] | Standard Reports | Custom Reports | Requires further clarifications
|  | List of Report Expand/Collapse (Example) | Management Reports
Favourite Reports
Report Details (Example)
Customise Reports (Exapand/Collapse)
D12 | Equipment screen | Equipment List | Equipment Details View | Requires further clarifications
Add Equipment Pop-up
D13 | Gmail Integration | Mailbox | Integrated System Emails from System | Requires further clarifications
Mail Details
Send Gmail
Mail Compose Box
Push Mail Folders
Delete Email
D14 | Calendar Integration | Calendar UI (without Integration with Time Tracking Function for Job and Employee) | Time tracking | Requires further clarifications
Get Calendar List
Calendar View for Day/Week/Month/Year
Create/Edit/Delete Event
Event Details
D16 | Customer Relationship Management (CRM) | Residential Contacts List: - Delete Selected - Export Selected to Excel format
Commercial Contacts List: - Delete Selected - Export Selected to Excel format
Residential Contact Details
Commercial Contact Details
Edit Residential Contacts
Edit Commercial Contacts
Add New Residential Contact
Add New Commercial Contact
Notes:
As some features still need further clarification so they will not be included in the Beta version of September and will be made up in October, hence total effort in Sep and Oct would be slightly different from original estimation.
But in general, this slight adjustment does not affect any Release Stages and Overall Team Effort of the project.
The module which supports to sync data with Quickbooks hasn't deployed to Stage enironment yet. We will deploy this module on this week.